## Sheet1
🔗 Requirement Traceability Matrix (RTM)
Req ID | Requirement Description | Module | Test Scenario ID | Test Case IDs | Bug IDs | Coverage Status | Remarks
REQ-001 | System shall allow creation of assessment questions with title, description, type, and options. | Assessment Questions | TS-001 | TC-001 | — | Covered | Basic CRUD verified
REQ-002 | System shall prevent creation of duplicate questions with identical titles. | Assessment Questions | TS-002 | TC-002 | BUG-001 | Failed | Duplicate detection missing
REQ-003 | System shall sanitize and properly display special characters in all text fields. | Assessment Questions | TS-003 | TC-003 | BUG-005 | Failed | XSS/encoding issue
REQ-004 | System shall retain all question data (including options) when editing. | Assessment Questions | TS-004 | TC-004 | BUG-009 | Failed | Options lost on edit
REQ-005 | System shall allow creation of test templates with multiple questions. | Test Templates | TS-005 | TC-005 | — | Covered | Basic creation works
REQ-006 | System shall update the question count in real-time when template is modified. | Test Templates | TS-006 | TC-006 | BUG-002 | Failed | Count stale until refresh
REQ-007 | System shall prevent deletion of templates that have dependent tests. | Test Templates | TS-007 | TC-007 | BUG-006 | Failed | Cascade delete not handled
REQ-008 | System shall enforce input validation on template names (character limit). | Test Templates | TS-008 | — | BUG-012 | Partial | No test case yet; bug confirmed
REQ-009 | System shall allow creation of tests with all required fields. | Test Creation | TS-009 | TC-008 | — | Covered | Happy path works
REQ-010 | System shall validate that test name is not empty before saving. | Test Creation | TS-010 | TC-009 | BUG-003 | Failed | No name validation
REQ-011 | System shall enforce a character limit on test description fields. | Test Creation | TS-011 | TC-010 | BUG-007 | Failed | No limit enforced
REQ-012 | System shall preserve form field values after a validation error. | Test Creation | TS-012 | — | BUG-010 | Partial | Dropdown reset confirmed
REQ-013 | System shall allow scheduling of tests for valid future dates only. | Schedule Tests | TS-013, TS-014 | TC-011, TC-012 | BUG-004 | Failed | Past dates allowed
REQ-014 | System shall display timezone information during test scheduling. | Schedule Tests | TS-015 | — | BUG-008 | Partial | No timezone shown
REQ-015 | System shall prevent duplicate test scheduling for the same candidate. | Schedule Tests | TS-016 | TC-013 | BUG-011 | Failed | No duplicate check